Gairloch High School

Àrd-sgoil Ghearrloch

Over the last few years in the West Coast of Scotland is the increased feeling of rural isolation, leading to poor mental health in a small but significant percentage of our senior pupils.  The increasingly worrying trend is that young people in S1 are more often arriving with anxieties, behavioural issues and mental health issues. My aim is to enhance the nurturing approaches and improve wellbeing by developing a community resilience transition project.  By improving the experience of transition for our pupils, through focusing on wellbeing and resilience, I believe that this will equip our students with lifelong skills which will enhance their engagement in school life and provide a support in adult life, especially for those who have been identified with adverse childhood experiences.  This should foster more positive relationships, and provide opportunities to allow improvement in attainment and development of key skills for the most vulnerable of our young people. In addition to our traditional three day transition, I wish to build in an extended period of transition, beginning in March 2019, not only providing a greater support to our new pupils, but by enabling a “Young Leader” experience for our S2 pupils to help them to gain further skills development, and focus on their own resilience.

Baseline assessment of Health & Wellbeing Wheel, attendance and behaviour analysis of pupils.

Follow on surveys and Questionaires.  Attendance and behaviour analysis.

1.3 Leadership of change

2.6 TRANSITIONS

2.7 Partnerships

3.1 ENSURING WELLBEING, EQUALITY AND INCLUSION

The Unfolding Story

# Planning

- ASG MEETINGS to go over the work, and support the plan

- Find a suitable resource/develop a resource that can work with both P7/S2

- Sharing the resource with the full team

- Timetabled delivery set up with all schools on board

- Baseline assessment of wellbeing wheel, staff and external agencies in the process.

- Using a range of evaluation techniques we will get everyone’s opinions.

- To produce a piece of work that can be shared with the schools, communicated with parents and celebrate the project in the P7 Induction.

- Include plan in the Newsletter

- Using Chromebooks to record the work completed in their P7 Profiles/S3 profile.

STANDARDS FOR HEADSHIP

4.1.4 Head Teachers collaborate with staff, learners, parents and the wider school community and networks in identifying, agreeing and implementing improvement priorities

PARTNERS: PRIMARY ASG,

HighLIfe HIGHLAND

I